## ProjectSchedule
MEDFINDER | [5 empty] | PROJECT GANTT CHART
Project: | Real-Time Medicine Availability & Store Locator | Project Start: | 2026-08-03
Team Members: | Madhav Gupta • Sourabh Chhabra • Arpit Yadav |  |  | Today: | 2026-09-06
|  | Display Week: | 1 |  |  |  | Week 1 (03 Aug) | [6 empty] | Week 2 (10 Aug) | [6 empty] | Week 3 (17 Aug) | [6 empty] | Week 4 (24 Aug) | [6 empty] | Week 5 (31 Aug) | [6 empty] | Week 6 (07 Sep) | [6 empty] | Week 7 (14 Sep) | [6 empty] | Week 8 (21 Sep) | [6 empty] | Week 9 (28 Sep) | [6 empty] | Week 10 (05 Oct) | [6 empty] | Week 11 (12 Oct) | [6 empty] | Week 12 (19 Oct) | [6 empty] | Week 13 (26 Oct) | [6 empty] | Week 14 (02 Nov) | [6 empty] | Week 15 (09 Nov) | [6 empty] | Week 16 (16 Nov) | [6 empty] | Week 17 (23 Nov) | [6 empty] | Week 18 (30 Nov)
TASK | ASSIGNED TO | PROGRESS | START | END |  | DAYS | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
TASK | ASSIGNED TO | PROGRESS | START | END |  | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Phase 1 — Planning & Research | bar: DAYS
Finalize problem statement and project objectives | Madhav Gupta, Sourabh Chhabra | 100% | 2026-08-03 | 2026-08-04 |  | DAYS: 2
Research existing medicine availability systems | Madhav Gupta, Arpit Yadav | 100% | 2026-08-05 | 2026-08-07 |  | DAYS: 3
Prepare and Submit Project Proposal | All Members | 100% | 2026-08-08 | 2026-08-10 |  | DAYS: 3
Prepare and deliver Presentation for idea disclosure | All Members | 100% | 2026-08-09 | 2026-08-10 |  | DAYS: 2
Finalize technology stack and development plan | Sourabh Chhabra | 100% | 2026-08-12 | 2026-08-16 |  | DAYS: 5
Phase 2 — System Analysis & Design | bar: DAYS
Prepared Data Flow(DFD), UML and ER diagrams | Arpit Yadav | 100% | 2026-08-18 | 2026-08-23 |  | DAYS: 6
Prepared Activity diagrams | Madhav Gupta | 100% | 2026-08-19 | 2026-08-30 |  | DAYS: 12
Design MySQL database schema | Madhav Gupta | 100% | 2026-08-31 | 2026-09-07 |  | DAYS: 8
Design system architecture and module structure | Sourabh Chhabra | 100% | 2026-09-02 | 2026-09-12 |  | DAYS: 11
Define REST API structure and data flow | Sourabh Chhabra | 100% | 2026-09-04 | 2026-09-06 |  | DAYS: 3
Phase 3 — Backend & Database Development | bar: DAYS
Set up Spring Boot project and backend structure | Sourabh Chhabra | 100% | 2026-09-03 | 2026-09-12 |  | DAYS: 10
Implement MySQL tables, entities and repositories | Madhav Gupta | 100% | 2026-09-07 | 2026-09-08 |  | DAYS: 2
Developed robust backend infrastructure | Sourabh Chhabra | 100% | 2026-09-03 | 2026-09-08 |  | DAYS: 6
Develop medicine search and inventory APIs | Madhav Gupta | 100% | 2026-09-05 | 2026-09-10 |  | DAYS: 6
Implement availability, store-distance and locator APIs | Arpit Yadav | 100% | 2026-09-10 | 2026-09-12 |  | DAYS: 3
Phase 4 — Frontend | bar: DAYS
Set up React.js application and component structure | Sourabh Chhabra | 50% | 2026-09-11 | 2026-09-13 |  | DAYS: 3
Build login, registration and user interface | Sourabh Chhabra | 70% | 2026-09-11 | 2026-09-13 |  | DAYS: 3
Build medicine search and availability results screens | Sourabh Chhabra | 100% | 2026-09-11 | 2026-09-12 |  | DAYS: 2
Nearby store locator | Arpit Yadav | 30% | 2026-09-12 | 2026-09-12 | bar: DAYS; S
Integrated complex 3D animation | Madhav Gupta | 50% | 2026-09-10 | 2026-09-13 |  | DAYS: 4
Phase 5 — Integration, Testing & Finalization | bar: DAYS
0% | bar: T to S
0% | bar: S to S
0% | bar: T to S
0% | bar: T to T
0% | bar: W to M
Planning note: | Progress values above are suggested as of 6-Sep-2026 based only on the work you reported; update them to match your actual team progress.
Legend | Green = completed/progress; light blue = planned duration; yellow = today (6-Sep-2026)
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
MedFinder project technology: React.js frontend, Spring Boot (Java) backend, MySQL database, Google Maps for store location.
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.